## Slide 1: Q2Q3D Specifications, Requirements and Scope
Paul Brindza

## Slide 2: Q2Q3D Outline
Q2Q3 and Dipole Specifications
Q2Q3D Status
Q2Q3 and Dipole Contracts
Scope of Work JLAB
Scope of Work SigmaPhi
Contract Reviews
Contract Documentation

## Slide 3: SHMS 11 GeV/c Spectrometer Hall C- June 2016 New companion to the 25 Year old HMS 7.4 GeV/c spectrometer
11 GeV/c
5 x 10^-4 dP/P resolution
4 mStr. Acceptance
5.5 to 40 degrees
Momentum bite 20%

## Slide 4: SHMS Spectrometer- June 2016 detectors and magnet yokes

## Slide 5: SHMS Magnets and Systems
Cryo-Control Reservoirs
Cryogenics Infrastructure
D
Q3
Q2
Q1
HB
Warm Yoke steel
Magnet Supports
This talk:
Q2, Q3 & Dipole
Vendor = Sigma Phi
1 x 10-3 dP/P Resolution
4 mSr Acceptance
1 to 11 GeV/c
Power Supplies & Controls
Cryo-Control Reservoirs
Cryogenics Infrastructure

## Slide 6: SHMS Dipole/Q2/Q3
DIPOLE:
3.86 Tesla Cosine(Θ) dipole
Bath Cooled 1.2 Atm, 4.42K
60 cm warm bore
2.85 m EFL
11.2 Tm Integral B.dL
17 MJ stored Energy
11 GeV/c
Warm Iron Yoke: 126 Tons
Q2 (shown):
11.8 T/m cos(2Θ) Quad
Bath Cooled
1.2 Atm., 4.42K
60 cm. warm bore
1.64 m EFL
7.6 MJ stored Energy
Warm Iron Yoke: 72 Tons
Q3:
Identical to Q2 but runs at 7.9 T/m
Warm Iron Yoke: 18 Tons
Both use same conductor as dipole (Cu + SSC outer)
Dipole field joint

## Slide 7: SHMS Dipole Q2/Q3 Specifications @ 11 GeV/c
 | Q2 | Q3 | Dipole
Type | Cos 2θ | Cos 2θ | Cos θ
Field/grad | 11.8 T/M | 7.9 T/M | 3.9 T
EFL | 1.64 M | 1.64 M | 2.85 M
Energy | 7.6 MJ | 3.5 MJ | 17 MJ
Inductance | 1.14 H | 1.14 H | 2.86 H
Current | 3660 A | 2480 A | 3450 A
NI | 6.3 MAT | 4.2 MAT | 4.2 MAT
aperture | 60 cm Φ | 60 cm Φ | 60 cm Φ
Dump Volts | 270 V | 180 V | 240 V
Dump R | 0.075 Ω ( 50 msec delay) | 0.075 Ω ( 50 msec delay) | 0.075 Ω ( 50 msec delay)
Conductor Soldered cable in channel | 0.3x1.9 cm^2+ SSC outer | 0.3x1.9 cm^2+ SSC outer | 0.3x1.9 cm^2+ SSC outer
AHS Temp | 45 K ( 1.02E8 miits) | 34 K (4.8 E7 miits) | 70 K ( 2.3 E8 miits)

## Slide 8: SHMS Dipole and Quad Magnet Coils
SHMS Quad 2/3
8 Layer, 4 Dbl. Pancake
2 sector Cos. 2 Theta coil
Constant Perimeter ends
427 Turns/pole
SHMS Dipole
6 Layer, 3 Dbl. Pancake
2 sector Cos. Theta coil
Constant Perimeter ends
606 Turns/pole

## Slide 9: Q2Q3D Interface Specifications
JLAB Specified and provided the interface for:
  Cryogenics- Cryo Control Reservoir
  DC Power Supply- Danfysik ( 6 V, 4000 Amps)
  QD/QP- DF quench detector and energy dump
  Controls – Hall C PLC
  External Instrumentation- Pressure, LL, Vac, lead flow
  Internal sensors- detailed spec and wiring in Tech Spec
  Magnet operating conditions- 4.4 K 1.2 Bar

## Slide 10: ASME, Pressure, Leak, VCL and Cryo Spec’s
ASME BPV Section VIII design, fab, test, material certs, welders certs and documentation required- No U Stamp
Pressure Max HE 75 PSIG, Max LN2 75 PSIG
Pressure test – 90 PSIG He & LN2
Leak Test Spec- none at 1 x 10^-9 Atm cc/sec
Cryogenic QHe < 40 W, QN2 < 100 W
VCL 5 KA burnout resistant (1.8 LL/Hr/KA, 80mV)
VCL TESTED conduction limit ~ 3700 A > Q2Q3D Iop

## Slide 11: Hall C SHMS Magnets a Year Ago – June 2015
HB @ JLab
(MSU/FRIB)
Q1 @ JLab
(SMI, UK)
Dipole Trial Collaring
(Sigma Phi, France)
Q2 splicing
(Sigma Phi, France)
Q3 coil assembly
(Sigma Phi, France)

## Slide 12: SHMS Q1 and HB Status
Q1:
  Installed on SHMS
  Cooled down
  Power test to 3000 Amps or 110% of operational current
  Accepted 2015
HB:
  Installed on SHMS
  Cooled down
  Power test to 4000 Amps or 102% of operational current
  Accepted 2016

## Slide 13: Dipole , Q2 & Q3 April 2016

## Slide 14: Q3 & Dipole June 2016

## Slide 15: Q2 July & August 2016

## Slide 16: Q2 has landed! Norfolk VA 10/5/16

## Slide 17: Q2 in JLAB Hall C 10/8/16

## Slide 18: Q2 Mounted on the SHMS 10/9/16

## Slide 19: SHMS October 11, 2016 Q2 Installed with yoke

## Slide 20: Q2Q3Dipole Status
Q2 is in JLAB Hall C installed on SHMS and under vacuum- Yoke and Platform assembly underway
Dipole is in Antwerp waiting for its ship- ETA Virginia is 10/28/16
Q3 is complete, leak tested and final welding underway – shipping date is 10/31/16
Documentation
  FDR Drawings, analysis, reports- Complete
  Dipole manufacturing Doc. ~ 90 % complete
  Q2Q3 manufacturing Doc.~ 80 % complete

## Slide 21: Q2Q3 and Dipole Contracts
Two Fixed price Design Build Contracts placed with SigmaPhi as a result of a competitive “Best Vaaue” award process- world bidders list- Buy America Act
Bid documents included a JLAB Reference Conceptual Design(RCD) for both magnets including CAD models, TOSCA models, FEA, models, drawings, reports, test results
Dipole Contract awarded Aug 2010
Q2Q3 Contract awarded Oct 2010

## Slide 22: Q2Q3Dipole Contracts
Q2Q3D were 4 year contracts now about 6 years
Q2Q3D fixed price contracts ~ 20% delta
  Extra scope items- consolidation and tests
  Productivity investments- extra tooling and shifts
  Storage of JLAB excess conductor and tooling
  Negotiated costs for extra work and problems

## Slide 23
Cryogenic Control Reservoir
Meyer Tool
Complete
FAB Magnets
Q1 accepted
HB accepted
Q2Q3 & Dipole Complete
Fixed Price Procurements
Q1 awarded SMI
HB awarded MSU
DQ2Q3 awarded Sigma Phi
Conductor Processing
HB & Q1 complete
Q2/Q3/D extrusion (FMM) Done
Wave soldering (AES) Done
Testing at BNL Complete
SC Cable (DOE SSC surplus)
DC Power System
Danfysik- Complete
Magnet Control System JLAB
Complete
Ship to JLAB
HB, Q1, Q2 Complete
Dipole on the way
Q3 ETA 11/30/16
On Site assembly & Integration by JLAB
HBQ1 Complete
Q2 underway
Acceptance Testing at JLAB on SHMS
Q1,HB accepted
Q2Q3D TBD
Magnet Support & Alignment
Complete
Iron Yoke castings
Ningbo-Jansen
Complete Machining
Craft-Hampton VA
Complete
SHMS SC Magnet System Plan

## Slide 24: Scope of Work - JLAB
RCD provided by JLAB
Conductor
  Superconductor( surplus SSC outer 32 strand cable)
  Copper Stabilizer( copper channel extrusion - FreeportMcMoran
  Soldering( AES, Allentown PA)
Cryo-Control Reservoir(CCR)- Meyer Tool & Mfg.
Burnout Resistant Vapor Cooled Leads, Mfg. & Testing (AMI)
DC Power Supply (DCPSU)- Danfysik
Quench protection and Detection- Danfysik
PLC controls, instrumentation read out, logging-JLAB Hall C
Warm Yoke- Ningbao-Jensen & Craft Machine
All on site installation and assembly except soldering dipole SC bus-Hall C
All on site services for Acceptance Testing (labor, cryogenics, AC power)
Plus all the free advice the contractor can stand!

## Slide 25: Scope of Work - SigmaPhi
Q2Q3 and Dipole Design and Analysis thru manufacturing drawings including ASME
Design & build all manufacturing tooling
Design all manufacturing processes
Design and perform all QA,QC, Inspections and Tests
Preliminary, Intermediate and Final Design reviews
Q2Q3D Documentation
Attend and present at ERR review ( today)
Integrate JLAB items (SC, CCR, VCL’s) into Q2Q3D
Attend Magnet Arrival Tests and Acceptance tests

## Slide 26: Scope of Work SigmaPhi II
Manufacture Q2Q3D SC magnets
  Consolidate conductor ( contract mod)
  Wind coils
  Vacuum impregnate coils
  Assemble coils into cold masses
  Collar coils
  Magnet instrumentation( Volt Taps, LHE&LN2 Temp. sensors, strain gauges)
  ASME Code test and documentation- Apave
  Fabricate cryostats- SDMS
  Final magnet assembly
  Pack and ship to JLAB Hall C

## Slide 27: Summary
Fixed price contracts for Q2Q3 and Dipole have born fruit!
Magnet installation has begun for Q2
Dipole is on its way and Q3 is ready to ship
Q2 Cool Down begins in ~ four weeks
Q2 Low Power Testing begins in ~ 6 weeks
Q3 Testing Jan 2017
Dipole testing Feb 2017

## Slide 28: Appendix VCL test results

## Slide 29: PIX of Burnout proof VCL’s

## Slide 30: Development of Burnout Proof Current Leads for SHMS Magnets
AMI/JLAB 5000 AMP burnout proof re-optimized vapor cooled current lead (1.63 L/Hr/KA)
5 KA lead pair designed, built and tested by AMI
5000 A DC No Cooling for 11.3 minutes Safe
3700 A DC No Cooling Safe forever
33 minute (2.5 A/sec)slow dump no cooling safe
We required a safe 15 Minute slow dump non cooled discharge!

## Slide 31: No burnout VCL 5 KA no coolant 11 min. test results

## Slide 32: No burnout VCL discharge test results

## Slide 33: Appendix 2 SSC Cable tests

## Slide 34: SSC Outer Cable Tests
12 samples of SSC outer cable tested at BNL
Test Conditions ~ SHMS Magnets
Field Range B ( 6T, 7T, 8T)
Current 0 < I < 11,000
Tests at 4.2 K
Results compare favorably to nominal short sample curve Ic=31532(1-B/15)^2.315 L. Dresner
Typical Ic twice (or thrice) Io at constant B

## Slide 35: SSC Outer Cable Measurements at 4.2 K

## Slide 36: Cable Tests, Nominal SSC Outer Short Sample Curve & SHMS Dipole Peak Field Load line

## Slide 37: SHMS Dipole and Q23 temp margins

## Slide 38: SHMS Q1' and HB Temp margins

## Slide 39: SHMS Operating Margins on Peak Field Load Line
 | Temp K | Current Ratio A Ic/Io | Field T | Energy J/M
HB | 3.31 | 3408 (1.77) | 2.91 | 0.088
Q1' | 3.86 | 4659 (1.46) | 3.92 | 0.213
Q23 | 2.18 | 1217 (1.24) | 1.43 | 0.480
Dip | 2.34 | 1552 (1.35) | 1.68 | 0.528