N°1-24 April 2013 – Final Design Report, milestone D4

DOCUMENTS SUBMITTED FOR APPROVAL:

D4-Final Design Review:

D5-QA/QC

D7-Magnetic Analysis

D8-Stress Analysis

D9-Quench Analysis

D10-Quench protection

D11-Pressure analysis

D11-Drawings package

Assembly

Coil

Conductor

Cold mass

Outer vessel

Radiation Screen

Helium Vessel

Force rings

Transport suspension

Suspensions Links

PID

CUSTOMER ANSWERS:

Please send back directly this document by e-mail to  fforest@sigmaphi.fr

Caution: reply time longer than 2  weeks  may postpone the magnet delivery time

Caution: new request made after approval may add extra-cost in time design and manufacturing

- Items listed  above are APPROVED with the following comments:

To do list to complete the documents before manufacturing:

Contract

- Amendment about the risks sharing related to the conductor

D5-QA/QC

- Update the documents with :

- Conductor  consolidating process

- Coil vacuum impregnation process

- Vessel parts subcontracting

- Completion date: 19/07/2013

D6-Magnet traveler

To be done

- Completion date:19/07/2013

D7-Magnetic analysis

- Update the Opera model with  the turns layout based on the  consolidated conductor dimensions  to check the field harmonics

- Completion date: 15 May 2013

D8-Stress analysis

- Upgrade the Ansys model with  the non linear stress/strain curve measured at 80K

- Do the simulation at several collaring temperatures to simulate the pre loading tolerances

- Completion date: 14 june 2013

D11-Pressure analysis

- Select the vessels parts subcontractor

- Completion date:  15 May 2013

- Complete the weld design review and analysis with the subcontractor

- Update the vessels drawings

- Complete the FEA calculations  and do the design  approval  with  Apave

- Completion date: 19 July 2013

- Do the welds qualification and welders qualification at the subcontractor facility

- Completion date: 18 October 2013

D15-Drawings package

- Modify the spacers geometry  to be consistent with the Opera model and the consolidated conductor dimensions

- Completion date: 15 May 2013

- Update the  welds design with the vessels parts subcontractor

- Validate the tolerances build up between the vessels inner bore

- Completion date: 19 July 2013

- Define some temporary collars to measure the real coil modulus and initial stress/strain lag

- Completion date: 19 July 2013

Customer Name:                                          Date: