## Instructions
Instructions for use

The spreadsheet is protected. Changes are allowed only in designated cells

Work only on “Tasks” page, ignore other pages

Cells that can be changed are shown in CLEAR background

Protected cells are greyed out

Please enter the actual duration of each actvity: enter times as HH:MM

Indicate completed activities with 100% in the corresponding column (enter 100, not 1)

The activities' names and descriptions can and should be changed to reflect the actual conditions

The GANTT charts are updated automatically as the activities are completed

Err:527 or charts not updating/no bars is caused by slow recalculation: JUST PRESS F9 to update worksheet (repeat as needed)

Please DON'T unprotect the document and make changes, ask the authors (see below)

Please ASK Oscar Rondon, Garth Huber or Cornel Butuceanu if you are unsure about any item

## Tasks
Info	No.	Activity Name - Zero Field Calibrations	Duration	Start	Finish	Complete	Done	Pending	Predecessors			Beam on Target	Auxiliary functions					Test column
	100	Elastic Calibrations	120:00	10/30 00:00	11/03 23:59	89%	10:51	13:08					Indices relative to ARRAYS, not row Nos.
	200	Set HMS to electrons	00:20	10/30 00:00	10/30 00:20	100%	00:20	00:00					0
	201	Beam energy measurement	03:00	10/30 00:00	10/30 03:00	0%	00:00	03:00					0
	202	HMS focal plane checkout; use C disk target	30:00	10/30 03:00	10/31 09:00	100%	06:00	00:00	200	201			2	10/30/08 12:20 AM	3	10/30/08 03:00 AM			10/30/08 03:00 AM		200
	203	Ask for 1 uA beam, 1 cm slow raster	00:10	10/31 09:00	10/31 09:10		00:00	00:10	202				4	10/31/08 09:00 AM					10/31/08 09:00 AM
	300	BigCal field OFF gain monitor ADC's	00:15	10/31 09:10	10/31 09:25		00:00	00:15	203				5	10/31/08 09:10 AM					10/31/08 09:10 AM		2
	310	Set HMS to protons 46.50°, p0 = 1.233 GeV. Start this at #300.	00:00	10/31 09:10	10/31 09:10	100%	00:00	00:00	203				5	10/31/08 09:10 AM					10/31/08 09:10 AM		$B$2
	311	Take 11k Elastic Coincidence events or run for >=	00:00	10/31 09:10	10/31 09:10	100%	00:00	00:00	310	203		00:00	7	10/31/08 09:10 AM	5	10/31/08 09:10 AM			10/31/08 09:10 AM		12:20:00 AM
	312	Set HMS to protons 43.1°, p0 = 1.360 GeV Start this at #300.	00:30	10/31 09:10	10/31 09:40		00:00	00:30	311				8	10/31/08 09:10 AM					10/31/08 09:10 AM
	313	Take 17k Elastic Coincidence events or run for >=	00:26	10/31 09:40	10/31 10:06		00:00	00:26	312			00:26	9	10/31/08 09:40 AM					10/31/08 09:40 AM
	314	Set HMS to 41.00°, p0 = 1.443 GeV	00:30	10/31 10:06	10/31 10:36		00:00	00:30	313				10	10/31/08 10:06 AM					10/31/08 10:06 AM
	315	Take 21k Elastic Coincidence events or run for >=	00:45	10/31 10:36	10/31 11:21		00:00	00:45	314			01:11	11	10/31/08 10:36 AM					10/31/08 10:36 AM
	316	Set HMS to 38.25°, p0 = 1.555 GeV	00:30	10/31 11:21	10/31 11:51		00:00	00:30	315				12	10/31/08 11:21 AM					10/31/08 11:21 AM
	317	Take 26k Elastic Coincidence events or run for >=	01:22	10/31 11:51	10/31 13:13		00:00	01:22	316			02:33	13	10/31/08 11:51 AM					10/31/08 11:51 AM
	318	Set HMS to 35.50°, p0 = 1.670 GeV	00:30	10/31 13:13	10/31 13:43		00:00	00:30	317				14	10/31/08 01:13 PM					10/31/08 01:13 PM
	319	Take 32k Elastic Coincidence events or run for >=	02:30	10/31 13:43	10/31 16:13		00:00	02:30	318			05:03	15	10/31/08 01:43 PM					10/31/08 01:43 PM		04/04/10
	320	Set HMS to 32.75°, p0 = 1.789 GeV	00:30	10/31 16:13	10/31 16:43		00:00	00:30	319				16	10/31/08 04:13 PM					10/31/08 04:13 PM		39746
	321	Take 18k Elastic Coincidence events or run for >=	03:00	10/31 16:43	10/31 19:43		00:00	03:00	320			08:03	17	10/31/08 04:43 PM					10/31/08 04:43 PM		0.00001157	0.0000000
	322	Set HMS to 30.00°, p0 = 1.907 GeV	00:30	10/31 19:43	10/31 20:13		00:00	00:30	321				18	10/31/08 07:43 PM					10/31/08 07:43 PM
	323	Take 4k Elastic Coincidence events or run for >=	04:30	10/31 20:13	11/01 00:43		00:00	04:30	322			12:33	19	10/31/08 08:13 PM					10/31/08 08:13 PM

		* Standard HMS momentum change time =	00:30

		NOTE: Scale counts by 1.5 for CH2 target
		Times already scaled with CH2/NH3 rate factor	0.667

Info	No.	Activity Name - Half Field 0deg Calibrations	Duration	Start	Finish	Complete	Done	Pending	Predecessors			Beam on Target
	350	Ramp target magnet to 2.5016 T - check field sign = +	00:30	11/01 00:43	11/01 01:13		00:00	00:30	323				20	11/01/08 12:43 AM					11/01/08 12:43 AM
	351	Ask for 1 uA beam, 1 cm slow raster, centered	00:10	11/01 01:13	11/01 01:23		00:00	00:10	350				31	11/01/08 01:13 AM					11/01/08 01:13 AM
	352	BigCal half field gain monitor ADC's	00:15	11/01 00:43	11/01 00:58		00:00	00:15					0		3
	353	Adjust BigCal HV; repeat gain monitor if needed **	01:00	11/01 00:58	11/01 01:58		00:00	01:00	352				33	11/01/08 12:58 AM					11/01/08 12:58 AM
	354	Set HMS to 46.50°, p0 = 1.233 GeV. Start this at #350.	00:30	11/01 00:43	11/01 01:13		00:00	00:30					0
	355	Take 9k Elastic Coincidence events or run for >=	00:13	11/01 01:23	11/01 01:36		00:00	00:13	354	351	352	00:13	35	11/01/08 01:13 AM	32	11/01/08 01:23 AM	33	11/01/08 12:58 AM	11/01/08 01:23 AM
	356	Set HMS to 43.75°, p0 = 1.334 GeV	00:30	11/01 01:36	11/01 02:06		00:00	00:30	355				36	11/01/08 01:36 AM					11/01/08 01:36 AM
	357	Take 18k Elastic Coincidence events or run for >=	00:17	11/01 02:06	11/01 02:23		00:00	00:17	356			00:30	37	11/01/08 02:06 AM					11/01/08 02:06 AM
	358	Set HMS to 41.00°, p0 = 1.443 GeV	00:30	11/01 02:23	11/01 02:53		00:00	00:30	357				38	11/01/08 02:23 AM					11/01/08 02:23 AM
	359	Take 21k Elastic Coincidence events or run for >=	00:30	11/01 02:53	11/01 03:23		00:00	00:30	358			01:00	39	11/01/08 02:53 AM					11/01/08 02:53 AM
	360	Set HMS to 38.25°, p0 = 1.555 GeV	00:30	11/01 03:23	11/01 03:53		00:00	00:30	359				40	11/01/08 03:23 AM					11/01/08 03:23 AM
	361	Take 13k Elastic Coincidence events or run for >=	00:28	11/01 03:53	11/01 04:21		00:00	00:28	360			01:28	41	11/01/08 03:53 AM					11/01/08 03:53 AM
	362	Set HMS to 35.50°, p0 = 1.670 GeV	00:30	11/01 04:21	11/01 04:51		00:00	00:30	361				42	11/01/08 04:21 AM					11/01/08 04:21 AM
	363	Take 17k Elastic Coincidence events or run for >=	00:51	11/01 04:51	11/01 05:42		00:00	00:51	362			02:19	43	11/01/08 04:51 AM					11/01/08 04:51 AM
	364	Set HMS to 32.75°, p0 = 1.789 GeV	00:30	11/01 05:42	11/01 06:12		00:00	00:30	363				44	11/01/08 05:42 AM					11/01/08 05:42 AM
	365	Take 10k Elastic Coincidence events or run for >=	05:48	11/01 06:12	11/01 12:00		00:00	05:48	364			08:07	45	11/01/08 06:12 AM					11/01/08 06:12 AM

		** Set as 100% complete if it was actually done

Info	No.	Activity Name - Full Field 0deg Calibrations	Duration	Start	Finish	Complete	Done	Pending	Predecessors			Beam on Target					DATE/TIME / DATE TIME
	400	Ramp target magnet to 5.0033 T - check field sign = +	01:00	11/01 12:00	11/01 13:00		00:00	01:00	365				46	11/01/08 12:00 PM					11/01/08 12:00 PM				DATE/TIME
	401	Ask for 1 uA beam, 1 cm slow raster, centered	00:10	11/01 13:00	11/01 13:10		00:00	00:10	400				57	11/01/08 01:00 PM					11/01/08 01:00 PM
	402	BigCal full field gain monitor ADC's	00:00	11/01 12:00	11/01 12:00	100%	00:00	00:00					0		3
	403	Adjust BigCal HV; repeat gain monitor if needed **	00:00	11/01 12:00	11/01 12:00	0%	00:00	00:00	402				59	11/01/08 12:00 PM					11/01/08 12:00 PM
	404	Set HMS to protons 43.1°, p0 = 1.360 GeV Start this at #400.	00:30	11/01 12:00	11/01 12:30		00:00	00:30					0
	405	Take 19k Elastic Coincidence events or run for >=	00:30	11/01 13:10	11/01 13:40		00:00	00:30	404	401	403	00:30	61	11/01/08 12:30 PM	58	11/01/08 01:10 PM	60	11/01/08 12:00 PM	11/01/08 01:10 PM
	406	Set HMS to 41.00°, p0 = 1.443 GeV	00:30	11/01 13:40	11/01 14:10		00:00	00:30	405				62	11/01/08 01:40 PM					11/01/08 01:40 PM
	407	Take 24k Elastic Coincidence events or run for >=	00:48	11/01 14:10	11/01 14:58		00:00	00:48	406			01:18	63	11/01/08 02:10 PM					11/01/08 02:10 PM
	408	Set HMS to 38.25°, p0 = 1.555 GeV	00:30	11/01 14:58	11/01 15:28		00:00	00:30	407				64	11/01/08 02:58 PM					11/01/08 02:58 PM
	409	Take 29k Elastic Coincidence events or run for >=	01:30	11/01 15:28	11/01 16:58		00:00	01:30	408			02:48	65	11/01/08 03:28 PM					11/01/08 03:28 PM
	410	Set HMS to 35.50°, p0 = 1.670 GeV	00:30	11/01 16:58	11/01 17:28		00:00	00:30	409				66	11/01/08 04:58 PM					11/01/08 04:58 PM
	411	Take 37k Elastic Coincidence events or run for >=	02:41	11/01 17:28	11/01 20:09		00:00	02:41	410			05:29	67	11/01/08 05:28 PM					11/01/08 05:28 PM
	412	Set HMS to 32.75°, p0 = 1.789 GeV	00:30	11/01 20:09	11/01 20:39		00:00	00:30	411				68	11/01/08 08:09 PM					11/01/08 08:09 PM
	413	Take 22k Elastic Coincidence events or run for >=	03:00	11/01 20:39	11/01 23:39		00:00	03:00	412			08:29	69	11/01/08 08:39 PM					11/01/08 08:39 PM
	414	Set HMS to 30.00°, p0 = 1.907 GeV	00:30	11/01 23:39	11/02 00:09		00:00	00:30	413				70	11/01/08 11:39 PM					11/01/08 11:39 PM
	415	Take 8k Elastic Coincidence events or run for >=	05:41	11/02 00:09	11/02 05:50		00:00	05:41	414			14:10	71	11/02/08 12:09 AM					11/02/08 12:09 AM
	416	Target work: anneal - TE - polarize	00:00	11/02 05:50	11/02 05:50	100%	00:00	00:00	415				72	11/02/08 05:50 AM					11/02/08 05:50 AM

		** Set as 100% complete if it was actually done
		NOTE: Scale counts by 1.5 for CH2 target
		Times already scaled with CH2/NH3 rate factor	0.667
		Adjust prescale factors, BigCal thresholds and kinematics file for replays as needed

Info	No.	Activity Name - Half Field 180deg Calibrations	Duration	Start	Finish	Complete	Done	Pending	Predecessors			Beam on Target
	500	Ramp magnet down; Hall access to reverse lead polarity at target PS	02:00	11/02 05:50	11/02 07:50		00:00	02:00	416				73	11/02/08 05:50 AM					11/02/08 05:50 AM				DATE/TIME
	501	Ramp target magnet to 2.5016 T - check field sign = -	00:30	11/02 07:50	11/02 08:20		00:00	00:30	500				82	11/02/08 07:50 AM					11/02/08 07:50 AM
	502	Ask for 1 uA beam, 1 cm slow raster, centered	00:10	11/02 08:20	11/02 08:30		00:00	00:10	501				83	11/02/08 08:20 AM					11/02/08 08:20 AM
	503	BigCal half field gain monitor ADC's.	00:15	11/02 05:50	11/02 06:05		00:00	00:15					0		4
	504	Adjust BigCal HV; repeat gain monitor if needed **	01:00	11/02 06:05	11/02 07:05		00:00	01:00	503				85	11/02/08 06:05 AM					11/02/08 06:05 AM
	505	Set HMS to 46.50°, p0 = 1.233 GeV. Start this at #500	00:30	11/02 05:50	11/02 06:20		00:00	00:30					0
	506	Take 9k Elastic Coincidence events or run for >=	00:13	11/02 08:30	11/02 08:43		00:00	00:13	505	502	503	00:13	87	11/02/08 06:20 AM	84	11/02/08 08:30 AM	85	11/02/08 06:05 AM	11/02/08 08:30 AM
	507	Set HMS to 43.75°, p0 = 1.334 GeV	00:30	11/02 08:43	11/02 09:13		00:00	00:30	506				88	11/02/08 08:43 AM					11/02/08 08:43 AM
	508	Take 18k Elastic Coincidence events or run for >=	00:17	11/02 09:13	11/02 09:30		00:00	00:17	507			00:30	89	11/02/08 09:13 AM					11/02/08 09:13 AM
	509	Set HMS to 41.00°, p0 = 1.443 GeV	00:30	11/02 09:30	11/02 10:00		00:00	00:30	508				90	11/02/08 09:30 AM					11/02/08 09:30 AM
	510	Take 22k Elastic Coincidence events or run for >=	00:31	11/02 10:00	11/02 10:31		00:00	00:31	509			01:01	91	11/02/08 10:00 AM					11/02/08 10:00 AM
	511	Set HMS to 38.25°, p0 = 1.555 GeV	00:30	11/02 10:31	11/02 11:01		00:00	00:30	510				92	11/02/08 10:31 AM					11/02/08 10:31 AM
	512	Take 13k Elastic Coincidence events or run for >=	00:28	11/02 11:01	11/02 11:29		00:00	00:28	511			01:29	93	11/02/08 11:01 AM					11/02/08 11:01 AM
	513	Set HMS to 35.50°, p0 = 1.670 GeV	00:30	11/02 11:29	11/02 11:59		00:00	00:30	512				94	11/02/08 11:29 AM					11/02/08 11:29 AM
	514	Take 17k Elastic Coincidence events or run for >=	00:51	11/02 11:59	11/02 12:50		00:00	00:51	513			02:20	95	11/02/08 11:59 AM					11/02/08 11:59 AM
	515	Set HMS to 32.75°, p0 = 1.789 GeV	00:30	11/02 12:50	11/02 13:20		00:00	00:30	514				96	11/02/08 12:50 PM					11/02/08 12:50 PM
	516	Take 10k Elastic Coincidence events or run for >=	00:58	11/02 13:20	11/02 14:18		00:00	00:58	515			03:18	97	11/02/08 01:20 PM					11/02/08 01:20 PM

		** Set as 100% complete if it was actually done

Info	No.	Activity Name - Full Field 180deg Calibrations	Duration	Start	Finish	Complete	Done	Pending	Predecessors			Beam on Target
	600	Ramp target magnet to 5.0033 T - check field sign = -	00:30	11/02 14:18	11/02 14:48		00:00	00:30	516				98	11/02/08 02:18 PM					11/02/08 02:18 PM				DATE/TIME
	601	Ask for 1 uA beam, 1 cm slow raster, centered	00:10	11/02 14:48	11/02 14:58		00:00	00:10	600				110	11/02/08 02:48 PM					11/02/08 02:48 PM
	602	BigCal full field gain monitor ADC's if needed **	00:15	11/02 14:18	11/02 14:33		00:00	00:15					0		3
	603	Adjust BigCal HV; repeat gain monitor if needed **	01:00	11/02 14:33	11/02 15:33		00:00	01:00	602				112	11/02/08 02:33 PM					11/02/08 02:33 PM
	604	Set HMS to 43.75°, p0 = 1.334 GeV. Start this at #600.	00:30	11/02 14:18	11/02 14:48		00:00	00:30					0
	605	Take 19k Elastic Coincidence events or run for >=	00:20	11/02 14:58	11/02 15:18		00:00	00:20	604	601	602	00:20	114	11/02/08 02:48 PM	111	11/02/08 02:58 PM	112	11/02/08 02:33 PM	11/02/08 02:58 PM
	606	Set HMS to 41.00°, p0 = 1.443 GeV	00:30	11/02 15:18	11/02 15:48		00:00	00:30	605				115	11/02/08 03:18 PM					11/02/08 03:18 PM
	607	Take 24k Elastic Coincidence events or run for >=	00:32	11/02 15:48	11/02 16:20		00:00	00:32	606			00:52	116	11/02/08 03:48 PM					11/02/08 03:48 PM
	608	Set HMS to 38.25°, p0 = 1.555 GeV	00:30	11/02 16:20	11/02 16:50		00:00	00:30	607				117	11/02/08 04:20 PM					11/02/08 04:20 PM
	609	Take 29k Elastic Coincidence events or run for >=	01:00	11/02 16:50	11/02 17:50		00:00	01:00	608			01:52	118	11/02/08 04:50 PM					11/02/08 04:50 PM
	610	Set HMS to 35.50°, p0 = 1.670 GeV	00:30	11/02 17:50	11/02 18:20		00:00	00:30	609				119	11/02/08 05:50 PM					11/02/08 05:50 PM
	611	Take 37k Elastic Coincidence events or run for >=	01:47	11/02 18:20	11/02 20:07		00:00	01:47	610			03:39	120	11/02/08 06:20 PM					11/02/08 06:20 PM
	612	Set HMS to 32.75°, p0 = 1.789 GeV	00:30	11/02 20:07	11/02 20:37		00:00	00:30	611				121	11/02/08 08:07 PM					11/02/08 08:07 PM
	613	Take 22k Elastic Coincidence events or run for >=	02:00	11/02 20:37	11/02 22:37		00:00	02:00	612			05:39	122	11/02/08 08:37 PM					11/02/08 08:37 PM
	614	Set HMS to 30.00°, p0 = 1.907 GeV	00:30	11/02 22:37	11/02 23:07		00:00	00:30	613				123	11/02/08 10:37 PM					11/02/08 10:37 PM
	615	Take 8k Elastic Coincidence events or run for >=	03:45	11/02 23:07	11/03 02:52		00:00	03:45	614			09:24	124	11/02/08 11:07 PM					11/02/08 11:07 PM
	616	Target work: anneal - TE - polarize	08:00	11/03 02:52	11/03 10:52		00:00	08:00	615				125	11/03/08 02:52 AM					11/03/08 02:52 AM

		** If #602,603 are not needed, set BigCal HV as in #403 and set 602, 603 = 100% complete

## Old_Tasks
Info	No.	Activity Name û- Zero Field Calibrations	Duration	Start	Finish	Complete	Done	Pending	Predecessors			Beam on Target	Auxiliary functions					Test column		DATE/TIME
	100	Elastic Calibrations	120:00:00	10/25 00:00	10/29 23:59	68%	82:10	37:49					Indices relative to ARRAYS, not row Nos.
?	200	Set HMS to electrons	00:20	10/25 00:00	10/25 00:20	100%	00:20	00:00					0
?	201	Beam energy measurement	03:00	10/25 00:00	10/25 03:00	100%	03:00	00:00					0
	202	HMS focal plane checkout; use C disk target	06:00	10/25 03:00	10/25 09:00	40%	02:24	03:36	200	201			2	10/25/08 12:20 AM	3	10/25/08 03:00 AM			10/25/08 03:00 AM		200
	203	Ask for 1 uA beam, 1 cm slow raster	00:10	10/25 09:00	10/25 09:10		00:00	00:10	202				4	10/25/08 09:00 AM					10/25/08 09:00 AM
	300	BigCal field OFF gain monitor ADC's	00:15	10/25 09:10	10/25 09:25		00:00	00:15	203				5	10/25/08 09:10 AM					10/25/08 09:10 AM		2
	310	Set HMS to protons 46.50°, p0 = 1.233 GeV. Start this at #300.	01:00	10/25 09:25	10/25 10:25		00:00	01:00	300	202			6	10/25/08 09:25 AM	4	10/25/08 09:00 AM			10/25/08 09:25 AM		$B$2
	311	Take 11k Elastic Coincidence events or run for >=	00:12	10/25 10:25	10/25 10:37		00:00	00:12	310	203		00:12	7	10/25/08 10:25 AM	5	10/25/08 09:10 AM			10/25/08 10:25 AM		12:20:00 AM
	312	Set HMS to 43.75°, p0 = 1.334 GeV	00:30	10/25 10:37	10/25 11:07		00:00	00:30	311				8	10/25/08 10:37 AM					10/25/08 10:37 AM
	313	Take 17k Elastic Coincidence events or run for >=	00:17	10/25 11:07	10/25 11:24		00:00	00:17	312			00:29	9	10/25/08 11:07 AM					10/25/08 11:07 AM
	314	Set HMS to 41.00°, p0 = 1.443 GeV	00:30	10/25 11:24	10/25 11:54		00:00	00:30	313				10	10/25/08 11:24 AM					10/25/08 11:24 AM
	315	Take 21k Elastic Coincidence events or run for >=	00:30	10/25 11:54	10/25 12:24		00:00	00:30	314			00:59	11	10/25/08 11:54 AM					10/25/08 11:54 AM
	316	Set HMS to 38.25°, p0 = 1.555 GeV	00:30	10/25 12:24	10/25 12:54		00:00	00:30	315				12	10/25/08 12:24 PM					10/25/08 12:24 PM
	317	Take 26k Elastic Coincidence events or run for >=	00:55	10/25 12:54	10/25 13:49		00:00	00:55	316			01:54	13	10/25/08 12:54 PM					10/25/08 12:54 PM
	318	Set HMS to 35.50°, p0 = 1.670 GeV	00:30	10/25 13:49	10/25 14:19		00:00	00:30	317				14	10/25/08 01:49 PM					10/25/08 01:49 PM
	319	Take 32k Elastic Coincidence events or run for >=	01:40	10/25 14:19	10/25 15:59		00:00	01:40	318			03:34	15	10/25/08 02:19 PM					10/25/08 02:19 PM		04/04/10
	320	Set HMS to 32.75°, p0 = 1.789 GeV	00:30	10/25 15:59	10/25 16:29		00:00	00:30	319				16	10/25/08 03:59 PM					10/25/08 03:59 PM		39746
	321	Take 18k Elastic Coincidence events or run for >=	02:00	10/25 16:29	10/25 18:29		00:00	02:00	320			05:34	17	10/25/08 04:29 PM					10/25/08 04:29 PM		0.00001157	0.0000000
	322	Set HMS to 30.00°, p0 = 1.907 GeV	00:30	10/25 18:29	10/25 18:59		00:00	00:30	321				18	10/25/08 06:29 PM					10/25/08 06:29 PM
	323	Take 4k Elastic Coincidence events or run for >=	03:00	10/25 18:59	10/25 21:59		00:00	03:00	322			08:34	19	10/25/08 06:59 PM					10/25/08 06:59 PM

		* Standard HMS momentum change time =	00:30

				DATE TIME

Info	No.	Activity Name û- Half Field 0deg Calibrations	Duration	Start	Finish	Complete	Done	Pending	Predecessors			Beam on Target
	350	Ramp target magnet to 2.5016 T - check field sign = +	00:30	10/25 21:59	10/25 22:29		00:00	00:30	323				20	10/25/08 09:59 PM					10/25/08 09:59 PM
	351	Ask for 1 uA beam, 1 cm slow raster, centered	00:10	10/25 22:29	10/25 22:39		00:00	00:10	350				31	10/25/08 10:29 PM					10/25/08 10:29 PM
	352	BigCal half field gain monitor ADC's	00:15	10/25 22:39	10/25 22:54		00:00	00:15	351				32	10/25/08 10:39 PM					10/25/08 10:39 PM		3
	353	Adjust BigCal HV; repeat gain monitor if needed **	01:00	10/25 22:54	10/25 23:54		00:00	01:00	352				33	10/25/08 10:54 PM					10/25/08 10:54 PM
	354	Set HMS to 46.50°, p0 = 1.233 GeV. Start this at #350.	00:30	10/25 22:29	10/25 22:59		00:00	00:30	350				31	10/25/08 10:29 PM					10/25/08 10:29 PM
	355	Take 9k Elastic Coincidence events or run for >=	00:13	10/25 22:59	10/25 23:12		00:00	00:13	354	351	352	00:13	35	10/25/08 10:59 PM	32	10/25/08 10:39 PM	33	10/25/08 10:54 PM	10/25/08 10:59 PM
	356	Set HMS to 43.75°, p0 = 1.334 GeV	00:30	10/25 23:12	10/25 23:42		00:00	00:30	355				36	10/25/08 11:12 PM					10/25/08 11:12 PM
	357	Take 18k Elastic Coincidence events or run for >=	00:17	10/25 23:42	10/25 23:59		00:00	00:17	356			00:30	37	10/25/08 11:42 PM					10/25/08 11:42 PM
	358	Set HMS to 41.00°, p0 = 1.443 GeV	00:30	10/25 23:59	10/26 00:29		00:00	00:30	357				38	10/25/08 11:59 PM					10/25/08 11:59 PM
	359	Take 21k Elastic Coincidence events or run for >=	00:30	10/26 00:29	10/26 00:59		00:00	00:30	358			01:00	39	10/26/08 12:29 AM					10/26/08 12:29 AM
	360	Set HMS to 38.25°, p0 = 1.555 GeV	00:30	10/26 00:59	10/26 01:29		00:00	00:30	359				40	10/26/08 12:59 AM					10/26/08 12:59 AM
	361	Take 13k Elastic Coincidence events or run for >=	00:28	10/26 01:29	10/26 01:57		00:00	00:28	360			01:28	41	10/26/08 01:29 AM					10/26/08 01:29 AM
	362	Set HMS to 35.50°, p0 = 1.670 GeV	00:30	10/26 01:57	10/26 02:27		00:00	00:30	361				42	10/26/08 01:57 AM					10/26/08 01:57 AM
	363	Take 17k Elastic Coincidence events or run for >=	00:51	10/26 02:27	10/26 03:18		00:00	00:51	362			02:19	43	10/26/08 02:27 AM					10/26/08 02:27 AM
	364	Set HMS to 32.75°, p0 = 1.789 GeV	00:30	10/26 03:18	10/26 03:48		00:00	00:30	363				44	10/26/08 03:18 AM					10/26/08 03:18 AM
	365	Take 10k Elastic Coincidence events or run for >=	01:00	10/26 03:48	10/26 04:48		00:00	01:00	364			03:19	45	10/26/08 03:48 AM					10/26/08 03:48 AM

		** Set as 100% complete if it was actually done

Info	No.	Activity Name -û Full Field 0deg Calibrations	Duration	Start	Finish	Complete	Done	Pending	Predecessors			Beam on Target					DATE/TIME
	400	Ramp target magnet to 5.0033 T - check field sign = +	00:30	10/26 04:48	10/26 05:18		00:00	00:30	365				46	10/26/08 04:48 AM					10/26/08 04:48 AM
	401	Ask for 1 uA beam, 1 cm slow raster, centered	00:10	10/26 05:18	10/26 05:28		00:00	00:10	400				57	10/26/08 05:18 AM					10/26/08 05:18 AM
	402	BigCal full field gain monitor ADC's	00:15	10/26 05:28	10/26 05:43		00:00	00:15	401				58	10/26/08 05:28 AM					10/26/08 05:28 AM		3
	403	Adjust BigCal HV; repeat gain monitor if needed **	01:00	10/26 05:43	10/26 06:43		00:00	01:00	402				59	10/26/08 05:43 AM					10/26/08 05:43 AM
	404	Set HMS to 43.75°, p0 = 1.334 GeV. Start this at #400	00:30	10/26 05:18	10/26 05:48		00:00	00:30	400				57	10/26/08 05:18 AM					10/26/08 05:18 AM
	405	Take 19k Elastic Coincidence events or run for >=	00:20	10/26 06:43	10/26 07:03		00:00	00:20	404	401	403	00:20	61	10/26/08 05:48 AM	58	10/26/08 05:28 AM	60	10/26/08 06:43 AM	10/26/08 06:43 AM
	406	Set HMS to 41.00°, p0 = 1.443 GeV	00:30	10/26 07:03	10/26 07:33		00:00	00:30	405				62	10/26/08 07:03 AM					10/26/08 07:03 AM
	407	Take 24k Elastic Coincidence events or run for >=	00:32	10/26 07:33	10/26 08:05		00:00	00:32	406			00:52	63	10/26/08 07:33 AM					10/26/08 07:33 AM
	408	Set HMS to 38.25°, p0 = 1.555 GeV	00:30	10/26 08:05	10/26 08:35		00:00	00:30	407				64	10/26/08 08:05 AM					10/26/08 08:05 AM
	409	Take 29k Elastic Coincidence events or run for >=	01:00	10/26 08:35	10/26 09:35		00:00	01:00	408			01:52	65	10/26/08 08:35 AM					10/26/08 08:35 AM
	410	Set HMS to 35.50°, p0 = 1.670 GeV	00:30	10/26 09:35	10/26 10:05		00:00	00:30	409				66	10/26/08 09:35 AM					10/26/08 09:35 AM
	411	Take 37k Elastic Coincidence events or run for >=	01:47	10/26 10:05	10/26 11:52		00:00	01:47	410			03:39	67	10/26/08 10:05 AM					10/26/08 10:05 AM
	412	Set HMS to 32.75°, p0 = 1.789 GeV	00:30	10/26 11:52	10/26 12:22		00:00	00:30	411				68	10/26/08 11:52 AM					10/26/08 11:52 AM
	413	Take 22k Elastic Coincidence events or run for >=	02:00	10/26 12:22	10/26 14:22		00:00	02:00	412			05:39	69	10/26/08 12:22 PM					10/26/08 12:22 PM
	414	Set HMS to 30.00°, p0 = 1.907 GeV	00:30	10/26 14:22	10/26 14:52		00:00	00:30	413				70	10/26/08 02:22 PM					10/26/08 02:22 PM
	415	Take 8k Elastic Coincidence events or run for >=	03:47	10/26 14:52	10/26 18:39		00:00	03:47	414			09:26	71	10/26/08 02:52 PM					10/26/08 02:52 PM
	416	Target work: anneal - TE - polarize	08:00	10/26 18:39	10/27 02:39		00:00	08:00	415				72	10/26/08 06:39 PM					10/26/08 06:39 PM

		** Set as 100% complete if it was actually done

Info	No.	Activity Name -û Half Field 180deg Calibrations	Duration	Start	Finish	Complete	Done	Pending	Predecessors			Beam on Target					DATE/TIME
	500	Hall access to reverse lead polarity at target PS	02:00	10/27 02:39	10/27 04:39		00:00	02:00	416				73	10/27/08 02:39 AM					10/27/08 02:39 AM
	501	Ramp target magnet to 2.5016 T - check field sign = -	00:30	10/27 04:39	10/27 05:09		00:00	00:30	500				82	10/27/08 04:39 AM					10/27/08 04:39 AM
	502	Ask for 1 uA beam, 1 cm slow raster, centered	00:10	10/27 05:09	10/27 05:19		00:00	00:10	501				83	10/27/08 05:09 AM					10/27/08 05:09 AM
	503	BigCal half field gain monitor ADC's.	00:15	10/27 05:19	10/27 05:34		00:00	00:15	502				84	10/27/08 05:19 AM					10/27/08 05:19 AM		4
	504	Adjust BigCal HV; repeat gain monitor if needed **	01:00	10/27 05:34	10/27 06:34		00:00	01:00	503				85	10/27/08 05:34 AM					10/27/08 05:34 AM
	505	Set HMS to 46.50°, p0 = 1.233 GeV. Start this at #500	00:30	10/27 04:39	10/27 05:09		00:00	00:30	500				82	10/27/08 04:39 AM					10/27/08 04:39 AM
	506	Take 9k Elastic Coincidence events or run for >=	00:13	10/27 06:34	10/27 06:47		00:00	00:13	505	502	504	00:13	87	10/27/08 05:09 AM	84	10/27/08 05:19 AM	86	10/27/08 06:34 AM	10/27/08 06:34 AM
	507	Set HMS to 43.75°, p0 = 1.334 GeV	00:30	10/27 06:47	10/27 07:17		00:00	00:30	506				88	10/27/08 06:47 AM					10/27/08 06:47 AM
	508	Take 18k Elastic Coincidence events or run for >=	00:17	10/27 07:17	10/27 07:34		00:00	00:17	507			00:30	89	10/27/08 07:17 AM					10/27/08 07:17 AM
	509	Set HMS to 41.00°, p0 = 1.443 GeV	00:30	10/27 07:34	10/27 08:04		00:00	00:30	508				90	10/27/08 07:34 AM					10/27/08 07:34 AM
	510	Take 22k Elastic Coincidence events or run for >=	00:31	10/27 08:04	10/27 08:35		00:00	00:31	509			01:01	91	10/27/08 08:04 AM					10/27/08 08:04 AM
	511	Set HMS to 38.25°, p0 = 1.555 GeV	00:30	10/27 08:35	10/27 09:05		00:00	00:30	510				92	10/27/08 08:35 AM					10/27/08 08:35 AM
	512	Take 13k Elastic Coincidence events or run for >=	00:28	10/27 09:05	10/27 09:33		00:00	00:28	511			01:29	93	10/27/08 09:05 AM					10/27/08 09:05 AM
	513	Set HMS to 35.50°, p0 = 1.670 GeV	00:30	10/27 09:33	10/27 10:03		00:00	00:30	512				94	10/27/08 09:33 AM					10/27/08 09:33 AM
	514	Take 17k Elastic Coincidence events or run for >=	00:51	10/27 10:03	10/27 10:54		00:00	00:51	513			02:20	95	10/27/08 10:03 AM					10/27/08 10:03 AM
	515	Set HMS to 32.75°, p0 = 1.789 GeV	00:30	10/27 10:54	10/27 11:24		00:00	00:30	514				96	10/27/08 10:54 AM					10/27/08 10:54 AM
	516	Take 10k Elastic Coincidence events or run for >=	00:58	10/27 11:24	10/27 12:22		00:00	00:58	515			03:18	97	10/27/08 11:24 AM					10/27/08 11:24 AM

		** Set as 100% complete if it was actually done

				DATE/TIME

Info	No.	Activity Name û- Full Field 180deg Calibrations	Duration	Start	Finish	Complete	Done	Pending	Predecessors			Beam on Target
	600	Ramp target magnet to 5.0033 T - check field sign = -	00:30	10/27 12:22	10/27 12:52		00:00	00:30	516				98	10/27/08 12:22 PM					10/27/08 12:22 PM
	601	Ask for 1 uA beam, 1 cm slow raster, centered	00:10	10/27 12:52	10/27 13:02		00:00	00:10	600				110	10/27/08 12:52 PM					10/27/08 12:52 PM
	602	BigCal full field gain monitor ADC's if needed **	00:15	10/27 13:02	10/27 13:17		00:00	00:15	601				111	10/27/08 01:02 PM					10/27/08 01:02 PM		3
	603	Adjust BigCal HV; repeat gain monitor if needed **	01:00	10/27 13:17	10/27 14:17		00:00	01:00	602				112	10/27/08 01:17 PM					10/27/08 01:17 PM
	604	Set HMS to 43.75°, p0 = 1.334 GeV. Start this at #600.	00:30	10/27 12:52	10/27 13:22		00:00	00:30	600				110	10/27/08 12:52 PM					10/27/08 12:52 PM
	605	Take 19k Elastic Coincidence events or run for >=	00:20	10/27 14:17	10/27 14:37		00:00	00:20	604	601	603	00:20	114	10/27/08 01:22 PM	111	10/27/08 01:02 PM	113	10/27/08 02:17 PM	10/27/08 02:17 PM
	606	Set HMS to 41.00°, p0 = 1.443 GeV	00:30	10/27 14:37	10/27 15:07		00:00	00:30	605				115	10/27/08 02:37 PM					10/27/08 02:37 PM
	607	Take 24k Elastic Coincidence events or run for >=	00:32	10/27 15:07	10/27 15:39		00:00	00:32	606			00:52	116	10/27/08 03:07 PM					10/27/08 03:07 PM
	608	Set HMS to 38.25°, p0 = 1.555 GeV	00:30	10/27 15:39	10/27 16:09		00:00	00:30	607				117	10/27/08 03:39 PM					10/27/08 03:39 PM
	609	Take 29k Elastic Coincidence events or run for >=	01:00	10/27 16:09	10/27 17:09		00:00	01:00	608			01:52	118	10/27/08 04:09 PM					10/27/08 04:09 PM
	610	Set HMS to 35.50°, p0 = 1.670 GeV	00:30	10/27 17:09	10/27 17:39		00:00	00:30	609				119	10/27/08 05:09 PM					10/27/08 05:09 PM
	611	Take 37k Elastic Coincidence events or run for >=	01:47	10/27 17:39	10/27 19:26		00:00	01:47	610			03:39	120	10/27/08 05:39 PM					10/27/08 05:39 PM
	612	Set HMS to 32.75°, p0 = 1.789 GeV	00:30	10/27 19:26	10/27 19:56		00:00	00:30	611				121	10/27/08 07:26 PM					10/27/08 07:26 PM
	613	Take 22k Elastic Coincidence events or run for >=	02:00	10/27 19:56	10/27 21:56		00:00	02:00	612			05:39	122	10/27/08 07:56 PM					10/27/08 07:56 PM
	614	Set HMS to 30.00°, p0 = 1.907 GeV	00:30	10/27 21:56	10/27 22:26		00:00	00:30	613				123	10/27/08 09:56 PM					10/27/08 09:56 PM
	615	Take 8k Elastic Coincidence events or run for >=	03:45	10/27 22:26	10/28 02:11		00:00	03:45	614			09:24	124	10/27/08 10:26 PM					10/27/08 10:26 PM
	616	Target work: anneal - TE - polarize	08:00	10/28 02:11	10/28 10:11		00:00	08:00	615				125	10/28/08 02:11 AM					10/28/08 02:11 AM

		** If #602,603 are not needed, set BigCal HV as in #403 and set 603, 603 = 100% complete